## weekly_2020
2020-03-16 | [8 empty] | Note
| Mon |  | Tue | Wed | Tue | Fry | Sat | Sun
Dec 2019 | 2019-12-30 | Settimana 53 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05
Jan 2020 | 2020-01-06 | Settimana 2 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12
| 2020-01-13 | Settimana 3 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19
| 2020-01-20 | Settimana 4 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26
| 2020-01-27 | Settimana 5 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02
< Chinese New Year
Feb 2020 | 2020-02-03 | Settimana 6 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09
| 2020-02-10 | Settimana 7 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16
| 2020-02-17 | Settimana 8 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23
[6 empty] | USR contract signed |  |  |  | close the contract, NDA, and other starting bureaucracy with USR
| 2020-02-24 | Settimana 9 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | > Bilato 24-26/2
[6 empty] | USR elec.schem. |  |  |  | USR share with us a draft of electrical schematics
Mar 2020 | 2020-03-02 | Settimana 10 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08
[6 empty] | USR WiFI schematic check (TBC) |  |  |  | CAREL do a quick check on electrical schematics same week USR is able to start drawing the PCB | Concept
| 2020-03-09 | Settimana 11 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15
[5 empty] | USR contract signed | USR PCB design Ready | USR elec.schem. |  |  | end of this week the design of PCB is ready
| 2020-03-16 | Settimana 12 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22
| USR WiFI schematic check | [5 empty] | USR PCB Ready WiFi
| 2020-03-23 | Settimana 13 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29
[5 empty] | WiFi FW V.0,9 OTA to USR |  | USR PCB Ready 2G |  |  | end of week sample of PCB are ready in USR
| 2020-03-30 | Settimana 14 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05
[6 empty] | USR sample soldereed |  |  |  | end of week +/- 10 pcs of gateway are soldered.
Apr 2020 | 2020-04-06 | Settimana 15 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12
[6 empty] | Start HW validation |  |  | > Bilato 9-14/4 |  | Prototype
| 2020-04-13 | Settimana 16 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19
| 2020-04-20 | Settimana 17 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26
| USR finish wifi and 2G samples |  | WiFi FW V.1,0 OTA to USR |  |  | End HW validation |  |  |  | end of this week the HW is preliminary tested. Within this week CAREL HQ provide to USR the file of the technical leaflet to be put in the box.
| 2020-04-27 | Settimana 18 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03
|  |  | END GSM FW on demo board |  |  | Start Homologation |  |  |  | USR + CAREL China start the homologation test on the device.
May 2020 | 2020-05-04 | Settimana 19 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10
[10 empty] | end of this week we are able to understand if all the tests are passed in case of fails we need to replan the following points. | Design freeze
| 2020-05-11 | Settimana 20 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-16 | 2020-05-17
[10 empty] | end of this week if everything is ok USR is able to launch the production of the first batch of devices. | Preseries
| 2020-05-18 | Settimana 21 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24
| 2020-05-25 | Settimana 22 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31
[10 empty] | end of week the first batch is ready to send to Italy | SOP
Jun 2020 | 2020-06-01 | Settimana 23 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07
| 2020-06-08 | Settimana 24 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14
Vale 1WK
| 2020-06-15 | Settimana 25 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20 | 2020-06-21
| 2020-06-22 | Settimana 26 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-27 | 2020-06-28
| 2020-06-29 | Settimana 27 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05
Jul 2020 | 2020-07-06 | Settimana 28 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-11 | 2020-07-12
| 2020-07-13 | Settimana 29 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19
Ale 1WK
| 2020-07-20 | Settimana 30 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26
| 2020-07-27 | Settimana 31 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02
Aug 2020 | 2020-08-03 | Settimana 32 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09
| 2020-08-10 | Settimana 33 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16
| 2020-08-17 | Settimana 34 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23
Ale 1WK / Vale 1wk
| 2020-08-24 | Settimana 35 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30
| 2020-08-31 | Settimana 36 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06
Set 2020 | 2020-09-07 | Settimana 37 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13
| 2020-09-14 | Settimana 38 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20
| 2020-09-21 | Settimana 39 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27
| 2020-09-28 | Settimana 40 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04
Oct 2020 | 2020-10-05 | Settimana 41 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11
| 2020-10-12 | Settimana 42 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18
| 2020-10-19 | Settimana 43 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25
| 2020-10-26 | Settimana 44 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01
Nov 2020 | 2020-11-02 | Settimana 45 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08
| 2020-11-09 | Settimana 46 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15
| 2020-11-16 | Settimana 47 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22
| 2020-11-23 | Settimana 48 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29
| 2020-11-30 | Settimana 49 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06
Dec 2020 | 2020-12-07 | Settimana 50 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13
| 2020-12-14 | Settimana 51 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20
| 2020-12-21 | Settimana 52 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27
| 2020-12-28 | Settimana 53 | 2020-12-29 | 2020-12-30 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-03